## Sheet1
Week | <task component> | Difficulty
2022-09-10 | Create spreadsheet of project plan | Easy
| Create trello board | Easy
| Create Git repo | Easy
| Setup Azure Cloud shell, set up SSH keys, upload SSH keys to GitHub. | Easy
| Clone personal GitHub repo to Azure Cloud shell using ssh keys. | Easy
| Create sample project scaffolding to test if a basic CI is working. | Easy
| Enable github actions to test CI. Make some changes in the python-app.yml file and notice if the github action workflow is successfully executed or not. | Medium
| Take a screenshot of a successful GitHub action workflow run. | Easy
| Paste the GitHub actions badge to the readme file in github. | Easy
2022-09-17 | Replace the scaffolding code with the flask code | Medium
| Test if the Flask application is running locally in the cloud shell by executing the make_predictions.sh command. | Medium
| Create an azure webapp by running the command in the cloud shell. | Medium
| Test if the Flask app is running fine in the azure app service. | Medium
2022-09-24 | Push all the changes to personal Github repo. | Hard
| Create an azure devops organisation and azure devops project. | Medium
| Create a service connection to azure app service. | Medium
| Test the azure devops pipeilne, it should execute without errors. | Medium
2022-02-10 | Test if the azure app is working fine, by clicking on the website url and also running make_predict_azure_app.sh script in the cloud shell. | Hard
| Make some changes in the code in GitHub and see if the azure pipeline is picking up the change and deploying it or not. | Hard
2022-10-08 | Create architectural diagram | Medium
| Take screenshots demonstrating key steps | Easy
| Create README file with full instructions of how to run the code | Medium
| Create a screencast of all the steps and upload to youtube. | Medium
Goals
Submit project and get it reviewed.
Pass the project
Q4 plan | Submit the project
Yearly plan | Review the code and ensure it still works. Improvise on the app and work on backlogs.